## Slide 1
CNN Posit Accelerator
Project progress, current verification status, and next build steps
4
Arithmetic blocks implemented
3
MAC / PE layers started
2
Systolic integration issues open
1
Primary next goal
Focus: make the PE-to-array partial-sum interface compile and verify end-to-end.
Project progress snapshot | 01

## Slide 2
CNN POSIT ACCELERATOR
Project objective
Build a hardware accelerator for CNN workloads using posit arithmetic, moving from verified arithmetic primitives into a systolic compute core.
TARGET COMPUTE PATH
•
Posit decode
•
Multiply
•
Accumulate
•
Quire option
•
Array output
•
Arithmetic precision is being explored through both rounded posit MAC and wide-quire MAC paths.
•
The project has advanced beyond isolated modules into PE and systolic-array composition.
Project progress snapshot | 02

## Slide 3
CNN POSIT ACCELERATOR
Repository progress map
Reference
•
posit_encoder.py
•
posit_decoder.py
•
test vectors
Arithmetic
•
posit_decoder.v
•
posit_encoder.v
•
posit_multiplier.v
•
posit_adder.v
Compute
•
posit_mac.v
•
posit_quire_mac.v
•
pe.v
•
pe_quire.v
System
•
input_fifo.v
•
output_fifo.v
•
systolic_array*.v
•
systolic_core*.v
Status: the lower layers are mostly in place; the top-level systolic hierarchy needs interface cleanup.
Project progress snapshot | 03

## Slide 4
CNN POSIT ACCELERATOR
Arithmetic datapath is in place
posit input
→
decoder
→
mul / add
→
encoder
→
posit output
Quire MAC path
Products are accumulated in a wide fixed-point quire, then converted back to posit only at output. This avoids repeated rounding inside long dot products.
Project progress snapshot | 04

## Slide 5
CNN POSIT ACCELERATOR
Verification status from local testbenches
Chart: 
| MAC | FIFO | PE | Array | Core
Pass = 1 | 1 | 1 | 0 | 0 | 0
INTERPRETATION
•
posit_mac testbench passes the checked accumulation cases.
•
input/output FIFO tests pass reset, write, read, wrap, and clear behavior.
•
PE tests compile but fail expected timing/output checks.
•
Systolic array/core elaboration fails due to missing partial-sum ports.
Project progress snapshot | 05

## Slide 6
CNN POSIT ACCELERATOR
Systolic compute hierarchy has been started
01
Input FIFOs
Buffers activations per row
OK
02
Skew / row delay
Offsets rows for systolic timing
OK
03
PE array
Instantiates PE grid
WIP
04
Output alignment
Delays columns for output sync
WIP
Project progress snapshot | 06

## Slide 7
CNN POSIT ACCELERATOR
Current blockers
Interface mismatch
•
Core and testbenches expect psum_out style ports.
•
Array modules currently expose PE outputs but not the expected column partial-sum ports.
Pipeline expectation
•
PE test expectations do not match the registered two-stage datapath.
•
Need to decide whether to change PE timing or update tests around intended latency.
These are integration issues, not a sign that the whole project needs to restart.
Project progress snapshot | 07

## Slide 8
CNN POSIT ACCELERATOR
Next build steps
1
Lock PE contract
Choose exact partial-sum direction, latency, and whether the quire PE or rounded PE is the main path.
2
Fix array ports
Expose column psum outputs from systolic_array and systolic_array_quire.
3
Rebaseline tests
Update PE and array testbenches to the chosen pipeline timing.
4
Add controller
Create top-level FSM for load weights, stream activations, compute, and drain outputs.
5
CNN layer demo
Run one small convolution or matrix-multiply case against Python reference data.
Project progress snapshot | 08